Factors influencing labor productivity on construction sites. A state-of-the-art literature review and a survey.

Introduction

The productivity of a major industry like construction is of significant importance for the economic growth of a nation. According to the European Construction Industry Federation (2011), the construction industry constitutes 9.7% of the gross domestic product (GDP) in the European Union (EU) with a total construction value of 1186 billion in 2010, providing 6.6% of Europe’s total employment. This means that construction productivity must grow and should be the Holy Grail of construction research and development.

The term “productivity” is generally defined as the maximization of output while optimizing input. Borcherding and Liou, (1986) referred to Construction labor productivity (CLP) in terms of labor cost to the quantity of outputs produced. While Horner and Talhouni (1995) defined CLP in terms of earned hours. It relies on the establishment of a set of standard outputs or “norms” for each unit operation. Thus, a number of “earned” hours are associated with each unit of work completed. The difficulty with this concept however, is in establishing reliable “norms”, for setting standards. It also depends on the method used to measure productivity, and on the extent to which account is taken of all the factors which affect it.

A project specific model is normally represented by the following equation:

Productivity  =                        Output                             (Thomas et al. 1990).

Labor + Equipment + Material

Given the numerous definitions of productivity that published in the literature, the construction industry has reportedly demanded the development of an acceptable measures to site productivity (Thomas and Zavrski (1999); Rojas and Aramvareekul (2003); Love and Smith (2003); Abdel-Hamid et al. (2004); Cottrell (2006); Liao et al. (2011). The majority of construction companies do not have formal measures in place at site level. This is evident in a survey of 77 UK contractors by Chan and Kaka (2003) which revealed that, more than half of the contractors do not monitor productivity levels at project level. To address the issue, several attempts have been made to measure and benchmark the construction processes (Yeung et al 2013). However, Lin and Huang (2010) criticized previous techniques that were developed in 1980’s and 1990’s as they lack objectivity. In addition, Crawford and Vogl (2006) and Bröchner and Olofsson (2012) both criticized the methods as they fail to reflect how technologies can affect the calculated productivity rate. Thus, different methodologies have been developed in the new millennium for deriving baseline productivity from a variety of estimation such as index number based accounting methods; data envelop analysis (DEA), and econometric methods. All these methods have their strengths and weaknesses and researchers can choose the appropriate method to fit the purpose of their studies (Hanna et al 2002; Gulezian and Samelian 2003; Ibbs and Liu 2005; Park et al. 2005; Abdel- Razek et al. 2007; Xue et al 2008; Lin and Huang 2010;  Zhao and Dungan 2014).

The UK construction industry has typically witnessed low levels of productivity and it is considered one of the most daunting problems that is facing the industry (Alinaitwi et al. 2007).  According to Horner and Duff (2001) an increase of 10% in the UK construction labour productivity is equivalent to a saving of £1.5bn to the industry’s clients, sufficient to procure perhaps an additional 30 hospitals or 30 000 houses per year. To meet this challenge, the UK government has called to cut both the cost of construction and the whole-life cost of built assets by 33% and to deliver a 50% faster projects by 2025 (McMeeken, 2008). Therefore it is essential for contractors to rise to this challenge by increasing their productivity level and this requires the efficient use of labor, accurate and complete drawings, no delays in work, safe work and quality workmanship (Hughes and Thorpe, 2014).

This research has identified four main components as to the main causes of low productivity, these are: “technical” such as ineffective planning of the resources and building design; “social” such as the motivation of laborers on site; “managerial” such as leadership and project control; “contractual” such as the procurement method adopted for the project. Myers (2013) added four other causal factors that are related to the industry itself, these are, firstly, the construction industry struggles to generate quality staff. Secondly, construction projects are short term and lessons are not adopted after each job. Thirdly, the industry suffers from poor levels of investment and innovation and finally, technology is not embraced fully as with other sectors.

This research sets out to achieve two main objectives:

1. To review the state of the art and trends in construction productivity research that are classified under (1) pre-construction activities; (2) factors during construction; (3) managerial and leadership issues; (4) organizational factors; and (5) motivational factors.

2. Building on from the literature and with input from industry experts, to rank the relative importance of factors perceived by the industry to influence CLP in the UK. As labor forces, whether directly employed or subcontracted, are under the management and supervision of the contractor, the survey of this research has concentrated on collecting data from contractors and more specifically contract mangers and site managers. The outcomes can help practitioners to develop a wider and deeper perspective of the factors influencing the productivity of operatives and to provide guidance to project and construction managers for the efficient utilization of the labor force. The following sections present literature review, research method, results and conclusions.

Research Method

A two stage methodology was adopted for this research, these are:

Stage 1 (literature review) - In order to determine the major research outputs published in first-tier journals for the chosen topics, this research adopted similar methodology to those employed by Al-Sharif and Kaka (2004), Tsai and Wen (2005), Ke et al. (2009), Hong et al. (2012) and Yi and Chan (2014). The search engines, Emerald; business Source Premier; Science Direct and Sage Journals were selected to identify journals that have published the most construction productivity related articles. The search covered the period 1970-2014.  and was not limited to a particular country. The desktop search was further refined by making reference to the journal ranking list of Chau (1997) in the area of construction engineering and management.

Nine top-ranked construction journals were included in the first round of the desktop search stage: Construction Engineering and Management (JCEM), Journal of Management in Engineering (JME), Construction Management and Economics (CME), Engineering, Construction and Architectural Management (ECAM), International Journal of Project Management (IJPM, Journal of Productivity and Performance Management, Journal of Computing in Civil Engineering, Journal of Construction Innovation and Journal of Built Environment. ). These journals were selected because they are known to have frequently published scholarly papers in the field of CLP. Moreover, these they have been ranked highly by several research activists in construction management such as the list by Chau (1997).

The main international conference proceedings that were reviewed are the CIB (W65) and (ARCOM). Technical reports and occasional papers were also covered as they are comprehensive and often publish up-to-date information. These are the Institute of Civil Engineering (ICE), Chartered Institute of Building (CIOB), and Royal Institute of Chattered Surveyors (RICS). These conference proceedings and reports were selected as they are well known to have disseminated research findings in the field of construction management and economics.

A comprehensive desktop search was then conducted under the “title/abstract/keyword” field to provide a content analysis of productivity papers. Search keywords included: organizational; design; planning; scheduling; procurement methods; project manager; management information system; construction methods; human resources; material; equipment; overcrowding, skills; variation orders; waiting time; rework; motivation; technology; innovation and weather. These topics were chosen on the basis of previous literature in these related fields and their link with CLP. Moreover, papers with these specific terms included in the title, abstract, or keyword were considered to have fulfilled the requirements of this research study. In some cases, the search was narrowed down by combining keywords such as “equipment” AND “productivity”. As a result, a total number of 119 productivity related articles and reports were identified and for the purpose of this paper, the references listed below were selected for discussion as they directly fit the purpose of this paper.

After the compilation of the literature material, the author critically analysed the information with the view to identify i) Similarities in the findings of previous writers; ii) Common issues raised; iii) Differences or contradictions of statements made; iv) Criticisms made by previous writers.

Stage 2 – Following on from the literature review, date from a survey by the author was analyzed to show the factors impairing CLP. In that survey, face-to-face interviews were conducted with 36 professions (19 contract managers and 17 site managers) with the aid of a structured (close-ended) questionnaire. These personnel were selected because of their direct supervision, who is under daily interaction with operatives and who can afford to render a reasonably accurate judgment on the primary and relevant factors influencing construction labor productivity on site.

The questionnaire was divided into 5 sections and each section contained the relevant factors. For example, factors such as planning, scheduling, procurement method and design were grouped under “pre-construction activities”. Factors such as variation orders, overcrowding, material and equipment management were grouped under “activities during construction” and so. In the questionnaire, the respondents were asked to rate each factor by using a scale from one (1) to three (3) in order of importance. The range included ‘not an important determinant’ (given a value of 1) to ‘very important determinant’ (given a value of 3). The data gathered was then analyzed using the descriptive  method of analysis.

Forty-six factors that were included in the questionnaire and they were selected based on previous research on CLP (Horner et al. 1989; Yates and Guhathakurta 1993; Lim and Alum 1995; Kaming et al. 1997; Zakari et al. 1997; Kaming et al. 1998a, b; Makulsawatudom et al. 2004; Ng et al. 2004; Abdul Kadir et al. 2005; Nepal et al. 2006; Alinaitwe et al. 2007; Enshassi et al. 2007; Hanna et al. 2007; Kazaz and Ulubeyli 2007; Kazaz et al. 2008; Onukwube et al. 2010; Ibironke et al. 2011; Jarkas and Bitar 2012).

The questionnaire was first tested by interviewing five local contractors. The suitability of the form and areas of particular interest to each participant were highlighted and the set of factors were evolved from these interviews. Some modifications were made to the original questionnaire and the final version was sent to 80 contracting organizations, names of which were selected randomly from Newly Registered First 10 Chartered Building Companies. 36 contractors were willing to be interviewed, 19 were contract mangers working at head office and 17 were experienced site managers who had worked in the construction industry for over 10 years. The co-operated firms were large size companies which meant that the survey is totally confined to large organizations. However, the nature of the projects that the site managers were involved in varied in type (commercial and industrial) and in size (over £2m million to £20 million)

The data collected were analyzed using the Relative Importance Index (RII) technique.

The RII for each factor explored was calculated by the formula shown below:

RII =  3(n3) + 2(n2) + n1

3(n1+n2+n3)

where n1, n2 and n3 are the number of respondents who selected: 1, for no effect; 2, for moderate effect; 3, for very strong effect, respectively. The higher the value, the stronger the perceived effect of the productivity. Table 1 shows the groups of factors that were rated by the respondents.

## Literature review of factors affecting site productivity

Factors related to pre-construction activities

Design and Procurement methods

Engineering design improvements are still regarded as areas with high potential for productivity improvement. Designers and quantity surveyors can not be expected to have sufficient understanding of the best way in which contractor’s resources can be applied to improve productivity in terms of cost and speed (Hackett et al., 2007). As the design becomes more complex, the productivity rate is expected to be affected and the net result is that many designs are inefficient to build. Productivity can therefore be increased by design rationalization, improved management, mechanization and prefabrication.

The move away from the traditional forms of contract to new methods of procurement in the 1970’s was a step towards developing a more collaborative approach, which is heralded as producing greater efficiency in project outcomes. One way of looking at collaboration is to examine the relationship among members of the building team, another is at the whole supply chain management concept. Loosemore (2014) investigated subcontractors’ perspectives of barriers to improving productivity within the Australian construction industry including the impact of the supply chain and the role of the sub-contractor in improving productivity. He suggested that for a subcontractor, it is imperative that there is a strong relationship with the principal contractor, but more importantly that the sub-contractor can be seen to have an early involvement in design. It is therefore proposed by Hamouda and Abu-Shaaban (2014) that, in order to ensure that productivity is at its maximum, it must be taken into consideration at tendering and design stage. Productivity will be more difficult to improve once construction has begun.

Further information about the relationship between procurement methods, collaboration and productivity rate can be found in (Stainer, 1997; Cheetham and Lewis 2001; Eddie et al 2001; Ng et al 2002; Chan et al 2002; Kumaraswamy et al  2004; Cottrell 2006; Fernie and Thorpe 2007; Hackett et al. 2007; CIOB 2010; Nasirzadeh and Nojedehi, 2013; Fulford et al 2014; Hughes and Thorpe 2014). Almost all of these studies were consistent with their conclusions in that non traditional form of contracts, namely, design and build, management contracting and partnering would provide natural benefits such as successfully managed project, improved coordination, logistic, communications, closer relationship building, workplace relations and ethics. As Loosemore (2014) put it, “productivity will be improved when information is more trustworthy, when there are fewer changes and in a more controlled way, and when there is not indiscriminate information distribution.”

Preconstruction planning

During planning and execution of construction projects, project planners and managers make various assumptions with respect to execution of construction activities, availability of resources, suitability of construction methods, and status of preceding activities. However, not all of these assumptions are explicitly documented and verified before the construction activities start. Decisions made based on invalid assumptions can negatively impact the outcomes of construction projects, such as rework, activity delays, and extra material cost (Gao et al. 2014). This notion supports the findings of Naoum and Hackman (1996), Dejahang (2006) and Doloi (2008) who found that, ineffective project planning and design errors as the most crucial factors influencing productivity. These studies also suggested that workers' attitude towards high productivity may not be limited to purely financial rewards, but inherently linked to many other latent factors, namely planning and programming.

According to Liu et al. 2011, the first and fundamental management action is to reduce work flow variation from the plan.  Ballard et al. (2003) introduced the Last Planner System (LPS) to stabilize work flow, which has been applied in construction to improve construction labor productivity. LPS is a philosophy and a set of principles and tools designed to improve work flow reliability through better planning strategies (González et al. 2008). It has been implemented in many places in the U.S., Europe, South America, and Asia (Liu et al. 2011) and proved to be a successful tool. Several other planning tools were evaluated to improve the productivity of on-site operation such as the one by Pradhan and Akinci (2012) and Gong et al (2010). In addition, Cottrell (2006) presented a regression model that relates job site productivity to process improvement initiatives (PIIs) executed both before and during construction. Applied during early project stages, his model intended to help industry practitioners to predict the expected value of labor productivity based on certain inputs related to preconstruction planning and construction execution. The model demonstrates the strong relationship of project performance to a variety of PIIs including design completeness, definition of a project vision statement, testing oversight, and project manager experience and dedication. The model provides project managers as front line industry practitioners with a deliberate yet practical approach to project management and productivity enhancement.

Selection of type and method of construction

Several research have been carried out to measure the productivity rate of various construction methods such as comparing the productivity rate of concreting as opposed to steel structure and the productivity rate of different types of frameworks used in construction. For example, Jarkas (2012) explored the influence of primary buildability factors on concreting labor productivity and a sufficiently large volume of productivity data was collected and analyzed by using the categorical-regression method. His findings showed that there are four significant impacts of factors that can influence the efficiency of the concreting operation. These are (1) concrete workability; (2) reinforcing steel congestion; (3) volume of pours; and (4) height relative to ground level, on labor productivity of skipped and pumped placement methods.

Off-site production of building components has become significantly more labor productive, in contrast to related on-site activities in the USA. Eastman and Sacks (2008) showed that, not only do they have a higher current level of labor productivity, but their rate of productivity growth overall is greater than comparable on-site sectors. In their sample, off-site productivity grew by 2.32% annually, while on-site productivity grew by 1.43%. Most of these studies suggested an improvement strategies in the area of mechanization and prefabrication.

Factors related to activities during construction

Material management on site

The management of material is a worldwide problem and has been cited as a major cause of productivity loss. Extensive multiple-handling of materials, materials improperly sorted or marked, trash obstructing access and movement of materials, running out of materials, and inefficient distribution methods are just a few instances of adverse material mismanagement conditions that have been reported by previous researchers (Thomas et al (1989); Abdul Kadir et al. 2005; Singh 2010 and El-Gohary and Aziz 2014). In an earlier study by Ferguson et al. (1995) in the UK, it was found that 50% of the waste deposited in disposal sites is construction waste. In order to reduce waste and increase productivity, the concept of Just-In-Time (JIT) was implemented on construction sites by early 1990’s and Pheng and Tan (1998) provided strong evidence to support the benefits of that concept. Moreover, Faniran and Caban (1998) suggested that wastage on site could be reduced if design changes were kept to a minimum during the construction work. The research also identified leftover material scraps, waste from packaging and un-reclaimable non-consumables, design/detailing errors, as being important sources of construction waste.

More recently, El-Gohary and Aziz (2014) presented an interesting summary table of factors affecting labor productivity across 10 countries. The factor “availability of the materials and their ease of handling” was discussed in most of the papers that were published. It had a weighting score of  90.34%, and therefore ranked second within the management group and third among all 30 factors that were surveyed. When considering uncertainty reduction and risk management in construction planning and control, Gao et al (2014) advocated that the stock and movement of material is the most frequently monitored information item in the last planner approach. Other factors included, the movement and status of equipment, the work flow and capability of crews, the status of prior work, the availability of construction information, the safety of external conditions, and the safety of the work space.

Equipment management on site

In addition to material management, construction productivity is also influenced by the management policy of the company regarding the selection of equipments and plants. In short, the policy on the type and number of equipments to use as well as getting the right balance between maintainability and replacement is a crucial decision making process by the company. Needles to say, equipments remain idle unless they are transformed into productive use by human performance. Previous research found substantial and statistically correlated longitudinal improvements in construction craft productivity associated with equipment improvements (Goodrum and Haas 2004; and Goodrum et al. 2009) as well as the timing of ordering the plants (Odeh and Battaineh 2002; Kazaz and Ulubeyli 2007). Through analysis of variance and regression, Goodrum and Haas (2004) found that activities experiencing significant changes in equipment technology have witnessed substantially greater long-term improvements in labor productivity than those that have not experienced a change.

Variation orders and changes of project scope

A considerable amount of research exists on the subject of construction variation orders and how it affects site productivity (Thomas et al. 1995; Thomas et al. 2003; Hanna et al. 1999; Hanna et al. 2005; Hanna et al. 2008; Ibbs 2005; Chang et al. 2007; Liu et al. 2011; Ibbs 2012). Disputes are common between the client and contractors when these changes.  A study by Hanna et al. (1999), used data from 43 projects and a linear regression model was developed that predicted the impact of changes on labor efficiency.  The model allows labor efficiency loss to be calculated in a particular project enabling both the client and the contractor to understand the impact such changes will have on labor productivity.  This research provided evidence to support the assertion that, disruption caused by changes in the original plan of work significantly increased the project cost through re-work and decreased labor efficiency for the main contractors and sub-contractors. Although Hanna’s study was limited to mechanical trade with some specific plumbing, fire protection, and process piping, their study corresponded closely with an earlier findings by Thomas and Napolitan (1995), Leonard (1987) and Zink (1990) who showed an average loss efficiency ranging from 10% - 30% as a result of changing orders. Interestingly, these studies realized that changes themselves do not directly decrease productivity or efficiency but rather, it is the manpower involved in the process.

Overcrowding

Site congestion and overcrowding are usually attributed to inappropriate construction site arrangement and overcrowding of the workers in some workplaces, which can cause obstructions to the desired productivity and quality.  According to Jarkas et al (2012), the overcrowding of workers usually results from inappropriate general planning of construction site activities. This issue has been reported by Watkins et al (2009); Dai et al (2009); El-Gohary (2014); Cottrell (2006); Borcherding and Alarcón (1991). Earlier, Smith (1987) provided evidence to suggest that a labor density greater than one man per 30 m2 will lead to a decrease in productivity. As working space deceases from 30 m2 (standard working space) to 10 m2 per operative, it incurs about a 40% productivity loss.

Skills of labor

Skill of labor has been investigated by Alinaitwe et al. (2007), Olomolaiye et al. (1998), Abdul-Wahab et al (2008), and Durdyev and Mbachu  (2011); Dai et al. (2009); Thomas and Horman (2006). According to Abdul-Wahab et al (2008), the effective utilization of skills rather than mere increase in the supply of skills is a key to bringing about productivity improvements. Indeed future policy makers should focus on addressing other influences on productivity performance such as work organisation and management practice to support further development and progression of the UK construction industry.

Factors related to management and leadership

The construction process is a collective effort involving a team of specialists from different organizations. Welfare of workers coupled with efficient management styles to control work activities from design to construction is essential to achieve high productivity (Ailabouni 2009). The success or failure of a construction project relies heavily on the effectiveness of the management of construction resources and the leadership style. Evidently, efficient management can yield substantial savings in time and cost (Shahata and Zayed 2011).  According to Rojas et al. (2003), the two areas identified as having the greatest potential for affecting productivity are management skills and manpower planning. Indeed, the managerial and leadership style can be seen as the umbrella that covers most of the factors discussed in this paper.

The leader of the team can affect the productivity of the design and construction and this also dependent upon the contractual arrangement adopted for the project. A number of studies have been conducted to investigate the relationship between leadership styles and productivity rate and found that charismatic and participative leadership behaviours primarily determine the satisfaction of the team members (Cheung et al. 2001). Moreover, leaders can have a significant role to play in fostering an innovation climate in construction firms that can lead to higher productivity. A study by by Chan et al (2014) revealed that transformation leadership is positively associated with innovation climate, whereas development exchange leadership is negatively associated with innovation climate. Here,

transformational leadership refers to four core dimensions: charisma (or idealized influence), inspiration stimulation, intellectual stimulation, and individualized consideration, while development exchange refers to the degree to which a leader establishes a system for followers to obtain contingent rewards for meeting an agreed on expectation.

Job satisfaction and motivational factors

Maloney (1986) defined motivation as the worker behavior with the objective of obtaining the means of satisfaction an unfulfilled need. While Lam and Tang (2003) defined motivation as the driving force that stimulates individuals physiologically and psychologically to pursue one or more goals to fulfill their needs or expectations. Since the 1940’s there has been a tremendous amount of work done to investigate the relationship between the individual and the company (extrinsic) motivation, as well as within the individual (intrinsic) motivation. The most relevant studies to construction are the ones conducted by Hazeltine (1976), Nicholla & Langford (1987), Ruthankoon and Ogunlana (2003), Kazaz and  Ulubeyli (2007) and Jarkas and Radosavljevic (2013). These articles differ with respect to the research strategy that they have adopted for their research. Most articles identified the key motivators being one or a combination of the following: salary, job security, high achievement, recognition, the nature of the work itself, responsibility and personal advancement and growth. Naturally, a key motivator for one worker compared with another worker in a certain situation may differ. The key question is whether there is a relationship between financial incentives, motivation and productivity. Critical appraisal of previous research related to construction seems to align with Herzberg's two-factor theory of motivation. The two factors are hygiene and motivators. In short, Hygiene factors such as money, supervision, status, security, working conditions, policies and interpersonal relations prevent dissatisfaction but do not motivate; they do not produce more output but prevent a decay in performance. Motivators such as work itself, recognition, advancement, possibility of responsibility and achievement can have a positive effect on job satisfaction which will lead to an increased output.

Organizational factors

Investment in technology and innovation

These factors are about applying new techniques, sciences and solutions to constructions. According to de Man (2008) innovation is “the process of bringing new creative ideas to reality and implementing them through new work practices, processes, business models and strategic partnerships to produce new products and services which are of value to society”. It has become essential for construction organizations to innovate because of increasing pressures from clients to improve productivity, quality, reduce costs and speed up construction processes. Management effectiveness can ultimately  determines profitability in most cases. According to Yi and Chan (2014), technology, including material and information technology, has had a tremendous effect on construction labor productivity over recent years. Tools, machinery, and the automation and integration of information systems have increased power and modified skill requirements (Hewage et al. 2008). Therefore, investing in technology and innovation is essential to productivity, cost effectiveness, and, more importantly, the sustainable development of any organization and industry. Following rapid globalization, technological advancement, and the trend toward partnering between the public and private sectors, the importance of innovation has increased dramatically for construction firms, particularly for large-size construction firms (Chan et al 2013).

An empirical research by Goodrum et al (2009) found that those activities that experienced significant changes in material technology have also experienced substantially greater long-term improvements in both their labor and partial factor productivity. Machinery has also become more powerful and complex (Goodrum et al (2004); Kannan (2011). It can therefore be argued that, information technology would revolutionize management information systems and help management obtain accurate information that leads to faster and more accurate decisions on site. According to Baldwin (1990), rapid mechanisation within the industry has resulted in increasing productivity by the introduction of structural steel, system form work, pre-casting techniques, pre-fabrication and component manufacture, but the construction industry requires more innovation to remain competitive among other sectors.

The survey

The section above has provided a state-of-the-art review of the development of CLP in the academic field. It has established a platform to obtain the perceptions of 37 contracting firms to the factors that can influence the rate of productivity on construction sites. Forty-six factors were identified and then classified under five primary categories: (1) pre-construction activities; (2) activities during construction; (3) management related factors; (4) organizational; and (5) motivational and social factors.

The RII ranks within the corresponding category are presented in Table 1. Primarily, it shows that ‘ineffective project planning’ and ‘delayed cause by design error and variations’ were top of the ranking list. This finding supports the earlier study of Borcherdings et al (1981) who stated that “the planning/design level is probably the key communication link in the hierarchy model between the “realities” of the site construction level and the “abstract” of the policy and programme management levels. The planning/design level becomes the controlling element in the industry’s effort to translate productivity information from above into a common language with a terminology meaningful to the desired audience”. Other highly ranked factors related to pre-construction activities are ‘the communication system adopted’; ‘Design and buildability related issues ’and ‘the Procurement method used for the project’.

The factors that seem to be of high importance to activities during construction are ‘lack of integration of the management information system for the project’; ‘management of material on site’; ‘control system’; ‘group co-ordination and overcrowding’; ‘ineffective site planning leading to program disruption and ‘supervision of subordinates’. This emphasizes the importance of designing an effective management information system (MIS) on site as it can be regarded as the linking mechanism of decision making, site supervision and communication. The productivity of a project depends on the management's access to accurate information to aid in timely decision making. Information which does not flow promptly from one group to another will cause rework and delays, hence, decreases productivity.

As far as mismanagement of material is concerned, comments from site managers indicated that most acute problems, caused by material mismanagement, are with material supply and storage, which can have a great impact on the sequence of work, and rework due to disruptions. This highly ranked factor corresponds closely with the recent work of El-Gohary and Aziz (2014) who emphasised that, timely delivery of material rather than the selection of the material is thought to be of high importance. This finding can also be linked with ‘project planning’ (before and during construction) which was ranked highly by the surveyed sample. With regard to ’disruption of site program’, this factor can cause delay in executing the work and prevent optimizing utilization of available resources. Timely input from all levels of management can reduce the risk of overlooking activities necessary to complete the project. Therefore delays contributing to lowering labor productivity can be reduced by planning the work to efficiently utilize manpower.

Under the managerial group, the surveyed sample regarded ‘management/leadership style’ and ‘project structure / authority and influence’ as highly important in affecting labor productivity on site. . These two factors cut across the managerial and the social aspects throughout the building process. The level of productivity attained by a firm is determined by a variety of organizational, technical and human factors, many of them directly controlled or influenced by management decisions. It could therefore be argued that a better site management can be associated with increased decentralization of decision making authority within the project, and with greater level of site manager influence over operations and decisions on site. This finding corresponds closely with the work of  Sanvido and Paulson (1992) who empirically tested the possible utilization of practical tools (from a productivity improvement view-point) that can support various theoretical decision-making phases. They demonstrated that, jobs where the planning and control functions were performed at the right level in the site hierarchy, were more profitable, finished sooner and were better constructed than those where the functions were performed at the wrong level of the hierarchy. Handy (1998) on the other hand, provided evidence that leadership styles are related to subordinate satisfaction, turnover and grievance rates as well as  intergroup conflict. There were cases in Handy’s research where supportive styles of leadership were found to be associated with higher producing work groups.

Several behavioral and psychological researches indicated that the expenditure of effort by a worker is the physical manifestation of motivation; the greater a worker’s motivation, the greater his/her expenditure of effort. Ranking on questions related to motivation shows that ‘work environment’ and ‘constraints on worker’s performance’ arising from ineffective management are more likely to affect labor performance at work and consequently influence site productivity. This finding is congruent with the very earlier conclusions of Borcherding & Ogglesby (1974) and Borcherding & Garner (1981) in that the major sources of dissatisfaction commonly expressed by both trades people and supervisors, are problems related to delay and reworking that affect the work place. According to Thomas et al (1989) frequently cited problems included the lack of tools, materials, delayed decisions, late information and changes in orders. The link between satisfaction and improved productivity is based upon the impact that such conditions are assumed to have on workers’ and supervisors’ motivation.

At organizational level, ‘experience of the selected personnel and training’ was ranked  rather high by the surveyed sample. Naturally, each task requires specific skills and knowledge of how to use these skills. Formal education and training programmes have been considered by previous researchers as a substitute for leadership, by developing individuals to work independently or with minimal supervision. Workers today are comparatively well educated, so training or teaching job skills is a necessity. Horner et al (1989) suggested that management must bear the burden of controlling the rapidly changing technological and social conditions, and that training programmes and methods of assessment must be relevant and appropriate to the needs of the organization. They must be designed and implemented in joint ventures between academia and industry. Indeed, ‘construction technology and method’ was also ranked fairly high by the surveyed sample and supports the findings Jarkas (2012) who showed that waiting time can significantly be reduced by adopting the appropriate method of construction to the operation and in turn affect the productivity level on site.

Conclusion

The subject of productivity and its relationship to project success has long been investigated and reported in academic journals. This paper reports on past and recent literature available on productivity in the construction industry. It sought to investigate the state of the art in productivity research and to survey the factors that can impair productivity on site. Whilst there has been some advancement in developing techniques and tools to measuring productivity, there seems to be a lack of investment in technology and innovation to improving productivity and thus more research and development should be conducted in this direction. Moreover, it was rather surprising not to capture research that directly linked the issue of productivity with the modern concepts of supply chain, lean construction, value engineering and BIM. Whilst there have been tremendous research into the applications of these concept, very little seem to have investigated their real impact on the rate of productivity on site. These concepts are, after all, directed toward eliminating waste, minimizing the transaction cost as well as the enhancement and transfer of shared knowledge and expertise among all parties.  Given the large number of computer software and systems available, this must be disheartening and reflects concerns that are raised by several articles reviewed in this paper. This issue seems to be more likely to be cultural and organizational.

Analysis of the survey results revealed that, contract and site managers perceive the rate of labor productivity on site is largely affected by activities related to the pre-construction stage of the building process, namely, ‘ineffective project planning’; ‘delays caused by design error and variations’; ‘the communication system adopted’; ‘design and buildability related issues including specifications’ and the ‘procurement method adopted’. This stresses the importance of integrating design and construction to achieving buildability and hence increasing productivity. This can be accomplished by increasing the awareness of the significant impact of allowing contractors to be involved at the preconstruction stage and to encourage the use of non-traditional procurement methods such as design and build, management contracting, project management and partnering. These methods facilitate the incorporation of the construction experience at the early stage of the building process so that the desired benefits can be achieved during the construction phase.

The surveyed sample also highly rated the factors that are associated with motivational and social issues, namely, ‘work environment’; ‘constraints on workers workmanship’ and ‘team cohesiveness and integration during construction. This reveals the importance of the quality of the working environment within the project that can influence the quality of work, productivity and laborers' motivation to work. This idea is also known as Quality Work Life (QWL). The philosophy behind it is that employees will normally be more productive if they actively enjoy the work experience, rather than just tailoring their lives at work. According to Naoum (2011), the main principle of a QWL is to change the climate or the culture of the workplace by allowing people to be more involved in the production process; improvement of environmental conditions; increasing the flow of communication within the work  place and 	better leadership styles and interpersonal relationships. Indeed, ‘management/leadership style’ and ‘project structure / authority and influence on site’ were highly ranked by the surveyed sample.

As a final remark, despite its high impact on the construction industry, productivity improvement is still an area in which much research work needs to be done to explore its true potential in a practical industry context. As Upul Ranasinghe et al. (2013) put it “today’s construction industry seems to adopt productivity improvement initiatives to gain a competitive edge in the global market place; however, systematization of these approaches is still an area of concern.”

# References

Abdel-Hamid, M., Abd Elshakour, H., Abdel-Razek, R. (2004), “Improving construction labor productivity in Egypt using benchmarking”, Banha Higher Institute of Technology, Banha, Egypt.

Abdul Kadir, M. R., Lee, W. P., Jaafar, M.  S., Sapuan, S. M., and Ali, A. A. A. (2005), “Factors affecting construction labor productivity for Malaysian residential projects”, Structural Survey, 23(1), 42-54.

Abdel-Razek, R. H., Abd-Elshakour, H., and Abdel-Hamid, M. (2007), “Labour productivity: Benchmarking and variability in Egyptian projects”, Int. J. Proj. Manage., 25(2), 189–197.

Abdel-Wahab, M. S., Dainty, A. R. J., Ison, S. G., Bowen, P., and Hazlehurst, G. (2008), “Trends of skills and productivity in the UK construction Industry”, J. Engineering, Construction and Architectural Management, 15(4), 372-382.

Ailabouni, N., Painting, N. and Ashton, P. (2009), “Factors affecting employee productivity in the UAE construction industry”, . Procs 25th Annual ARCOM Conference, 7-9 September 2009, Nottingham, UK, Association of Researchers in Construction Management, 555-64.

Alinaitwi, H., Mwakali, J. and Hansson, B. (2007), “Factors affecting the productivity of building craftsmen – studies of Uganda”, J. Construction Engineering and Management, Vol. 13 No. 3, pp. 169-176.

Allmon, E., Hass, C. T., Borcherding, J. D., and Goodrum, P. M. (2000), “U.S. construction labor productivity trends, 1970–1998”, J. Constr. Eng. Manage., 10.1061/(ASCE)0733-9364(2000)126:2(97), 97–104.

Al-Sharif, A., and Kaka, A. (2004), “PFI and PPP topic coverage in construction

journals”, Proc., 20th Annual ARCOM Conf., Vol. 1, Heriot Watt University, Edinburgh, Scotland, 711–719.

Arditi, D., and Mochtar, K. (2000), “Trends in productivity improvement in the US construction industry”, Journal of Construction management and economics, 18(1), 15-27.

Baldwin, A., (1990), Why an IT strategy is important?, Chartered Builder, July/August.

Ballard, G., Harper, N., and Zabelle, T. (2003) “Learning to see work flow:

Application of lean production concepts to precast concrete fabrication”, Eng. Construct. Architect. Manage., 10(1), 6–14.

Borcherding, J., and Oglesby, C. (1974), “Construction productivity and job satisfaction”, J. Constr. Div., ASCE, 100(3), 413–431.

Borcherding, J., and Garner, F. (1981), “Work force motivation and productivity on large jobs”, J. Constr. Div., ASCE, 107(3), 443–453.

Borcherding, J. D., Palmeter, S. B., and Jansma, G. L. (1986), Work force management programs for increased productivity and quality work, EEI Construction Committee Spring Meeting, 4–9

Borcherding, J. D., and Alarcón, L. F. (1991), “Quantitative effects on construction

productivity”, Constr. Lawyer (Am. Bar Assoc.), 11(1), 36–48.

Bröchner, J. (2010), Innovation in construction,  The handbook of innovation

and services: A multi-disciplinary perspective, F. Gallouj and F. Djellal, eds., Edward Elgar, Cheltenham, UK, 743–767.

Bröchner, J. and Olofsson, T. (2012), ”Construction Productivity Measures for Innovation Projects”, J. Constr. Eng. Manage., 138(5), 670–677. Case Studies

Chartered Institute of Building (2010),  “A report exploring procurement in the construction industry”, London, UK: CIOB.

Chan, .P, (2002), “Factors affecting labour productivity in the Construction Industry”, Department of Building Engineering and Surveying, Ph.D. Thesis, Heriot-Watt University, Edinburgh, UK.

Chan, P and Kaka, A (2003), “Construction labour productivity improvements”, Proceedings of the third international postgraduate research conference, 3 – 4 April, Escola Superior de Actividades Imobiliárias (ESAI), Lisbon, 583 – 598.

Chan, Y. S.; Liu, M.; and Fellows, F.  (2014), “Role of Leadership in Fostering an Innovation Climate in Construction Firms”, J. Manage. Eng., DOI: 10.1061/(ASCE)ME.1943-5479.0000271,

Chang, C. K., Hanna, A. S., Lackney, J. A., and Sullivan, K. T. (2007), “Quantifying the impact of schedule compression on labor productivity for mechanical and sheet metal contractor,” J. Constr. Eng. Manage., 10 .1061/(ASCE)0733-9364(2007)133:4(287), 287–296.

Chau, K. W. (1997), “The ranking of construction management journals”,  J. Constr. Manage. Econ., 15(4), 387–398.

Cheetham, D. W. and Lewis, J. (2001),” Productivity, buildability and constructability: is work study the missing link?”, 17th Annual ARCOM Conference, 5-7 September 2001, University of Salford. Association of Researchers in Construction Management, Vol. 1, 271-80.

Cheung, S. O., Ng, S. T., Lam, K. C., and Yue, W. M. (2001),” A satisfying leadership behaviour model for design consultants”, International Journal of Project Management, 19(7), 421-429.

Christian, J., and Hachey, D. (1995), “Effects of delay times on production rates in construction”, Journal of Construction Engineering and Management, ASCE, 121(1), 20-26.

Clarke, L., and Herrmann, G. (2004), “Cost vs. production: labour deployment and productivity in social construction in England, Scotland, Denmark and Germany”, Journal of Construction Management and Economics, 22(10), 1057-1066.

Crawford, P., and Vogl, B. (2006), “Measuring productivity in the construction industry”, Building Research and Information, 34(3), 208-219.

Cottrell, D., (2006), “Contractor Process Improvement for Enhancing Construction Productivity”, J. Constr. Eng. Manage., 10.1061/_ASCE_0733-9364_2006_132:2_189_196.

Dai, J., Goodrum, P. M., and Maloney, W. F. (2009), “Construction craft workers’ perception of the factors affecting their productivity,” J. Constr. Eng. Manage., 10.1061/(ASCE)0733-9364(2009)135:3(217), 217–226.

Dejahang, F., (2006), Determinate of Productivity Factors on Construction Sites, Ph.D. thesis, School of Built environment, London South Bank University.

# De Man, (2008), A Review of Knowledge Management and Innovation in Networks, Ard-Pieter (Ed.), Cheltenham, UK: Edward Elgar Publishing, Ltd., ISBN 978-1-8472-0230-7.

Doloi, H. (2008),“Application of AHP in improving construction productivity from a management perspective”, Journal of Construction Management and Economics, 26(8), 839-852.

Durdyev, S. and Mbachu, J. (2011), “On-site Labour Productivity of New Zealand Construction Industry: Key Constraints and Improvement Measures”, Australasian Journal of Construction Economics and Building, 11(3), 18-33.

Eastman, C. M., and Sacks, R. (2008), “Relative productivity in the AEC industries in the United States for on-site and off-site activities”, J. Constr. Eng. Manage., 10.1061/(ASCE)0733-9364(2008)134:7(517), 517–526.

Eddie W.L. Cheng, Heng Li, Peter E.D. Love, Zahir Irani, (2001),"An e-business model to support supply chain activities in construction", Logistics Information Management, Vol. 14 Iss 1/2 pp. 68 – 78.

El-Gohary, K., and Aziz, R., (2014), “Factors Influencing Construction Labor

Productivity in Egypt”, J. Manage. Eng., 10.1061/(ASCE)ME.1943-5479.0000168. 30:1-9.

Enshassi,  A., Mohamed, S., Mayer, P., and Abed, K. (2007), “Benchmarking Masonry Labor Productivity,” Journal of Productivity and Performance Management, 56(4), 358-368.

Faniran, O., and Caban, G.  (1998), “Minimizing waste on construction project sites. Engineering”, J. Construction, Engineering and Architectural Management, 5(2), 182-188.

Ferguson, J., Kermode, N., Nash, C. L., Sketch, W. A. J., and Huxford, R. P. (1995), “Managing and minimizing construction waste – A practical guide”, Institute of Civil Engineers, London.

Fernie, S. and Thorpe, A. (2007), “Exploring change in construction: supply chain management”, J. Engineering, Construction and Architectural Management, Vol. 14, No. 4, 2007, pp. 319-333.

Fulford, R. and Standing, C. (2014), “Construction industry productivity and the potential for collaborative practice”, International Journal of Project Management, 32 (2014), pp. 315-326.

Gao, T., Ergan, S., Akinci, B., and Garrett, J. (2014), “Understanding Characteristics of Assumptions Made for Construction Processes during Planning Based on Case Studies and Interview”, J. Constr. Eng. Manage., ASCE, (140).

Gong, J., Borcherding, J. D., and Caldas, C. H. (2011), “Effectiveness of craft time utilization in construction projects”, J. Constr. Manage. Econ., 29(7), 737–751.

González, V., Alarcón, L. F., and Mundaca, F. (2008), “Investigating the relationship between planning reliability and project performance”, Prod. Plann. Control Manage. Oper., 19(5), 461–474.

Goodrum, P., and Haas, C. (2004, “The long-term impact of equipment technology on labor productivity in the US construction industry at the activity level”, J. Constr. Eng. Manage., 10.1061/(ASCE)0733-9364(2004)130:1(124), 124–133.

Goodrum, P., Zhai, D., and Yasin, M. (2009), “Relationship between changes in material technology and construction productivity”, J. Constr. Eng. Manage., 135(4), 278–287.

Goodrum PM, Haas C T, & Caldas C. (2011),  “Model to predict the impact of a technology onconstruction productivity”, Journal of Construction Engineering and Management. 137(9) 678-688.

Gulezian, R., and Samelian, F. (2003), “Baseline determination in construction labour productivity-loss claims,” J. Manage. Eng., 10.1061/(ASCE) 0742-597X(2003)19:4(160), 160–165.

Hackett, M., Robinson, I. and Statham, G. (eds.) (2007) The Aqua Group Guide to Procurement, Tendering & Contract Administration. 4th ed. Oxford: Blackwell Publishing Ltd.

Hamouda H. and Abu-Shaaban, N. (2014), “Enhancing labour productivity within construction industry through analytical hierarchy process, the case of Gaza Strip”, Proceedings 30th Annual ARCOM Conference, 1-3 September 2014, Portsmouth, UK,  1335–44.

Hanna, A. S., Russell, J. S., and Vandenberg, P. J. (1999),“The impact of change orders on mechanical construction labour efficiency”, J. Construction Management & Economics, 17(6), 711-720.

Hanna, A. S., Lotfallah, W. B., and Lee, M. J. (2002), “Statistical fuzzy approach to quantify cumulative impact of change orders”, J. Comput. Civ. Eng., 10.1061/(ASCE)0887-3801(2002)16:4(252), 252–258.

Hanna, A. S., Taylor, C. S., and Sullivan, K. T. (2005), “Impact of extended overtime on construction labor productivity”, J. Constr. Eng. Manage., 10.1061/(ASCE)0733-9364(2005)131:6(734), 734–739.

Hanna, A., Chang, C., Sullivan, K., and Lackney, J. (2008), “Impact of shift work on labor productivity for labor intensive contractor”, J. Constr. Eng. Manage., 10.1061/(ASCE)0733-9364(2008)134:3(197), 197–204.

Hester, W., and Kuprenas, J. (1987), The productivity of insulation installation.

Hewage, K. N., Ruwanpura, J. Y., and Jergeas, G. F. (2008), “IT usage in Alberta’s building construction projects: Current status and challenges,” Autom. Constr., 17(8), 940–947.

Hazeltine, C. (1976), “Motivation of construction workers”, J. Constr. Div., 102(3), ASCE, 102, 497–509.

Hong, Y. M., Chan, W. M., Chan, P. C., and Yeung, F. Y. (2012), “Critical analysis of partnering research trend in construction journals”, J. Manage. Eng., 10.1061/(ASCE)ME.1943-5479.0000084, 82–95.

Horman, M. J., and Kenley, R. (2005), “Quantifying levels of wasted time in construction with meta-analysis”, J. Constr. Eng. Manage., 10.1061/ (ASCE) 0733-9364(2005)131:1(52), 52–61.

Horner, R.M.W., Talhouni, B.T., and Thomas, H.R. (1989), “Preliminary results of major labour productivity monitoring programme”, proceedings of the 3rd Yugoslavian Symposium on Construction Management, Cavtat

Horner, R. M. W., and Talhouni, B. T. (1995), “Effects of Accelerated Working, Delays, and Disruptionson Labor Productivity”,  Chartered Institute of Building, London.

Hughes R., Thorpe D. (2014), “A review of enabling factors in construction industry productivity in an Australian environment”, Construction Innovation, 14 (2), pp.210 – 228

Ibbs, W., and Liu, M. (2005), “Improved measured mile analysis technique”, J. Constr. Eng. Manage., 10.1061/(ASCE)0733-9364(2005) 131:12(1249), 1249–1256.

Ibbs, W. (2005), “Impact of change’s timing on labor productivity”, J. Constr. Eng. Manage., 10.1061/(ASCE)0733-9364(2005)131:11 (1219), 1219–1223.

Ibbs, William (2012), “Construction Change: Likelihood, Severity and Impact on Productivity", Journal of Legal Affairs and Dispute Resolution in Engineering and Construction. 4(3), August, 67-73.

Ibrahim, M., (2013), "Contractors perspective toward factors affecting labor productivity in building construction“,  J. Engineering, Construction and Architectural Management, Vol. 20 Iss: 5, pp.446 - 460

Jarkas, A. (2012), “Buildability factors influencing concreting labour productivity”, J. Constr. Eng. Manage., 138(1), 89–97.

Jarkas, A., and Bitar, C. (2012). “Factors affecting construction labor productivity in Kuwait.” J. Constr. Eng. Manage., 138(7), 811–820.

Jarkas, A. and Radosavljevic, M. (2013). ”Motivational Factors Impacting the Productivity of Construction Master Craftsmen in Kuwait.” J. Manage. Eng., 29(4), 446–454. Case Studies.

Kumaraswamy M. P., Love E.D., Dulaimi M., Rahman M. (2004),“Integrating procurement and operational innovations for construction industry development”, Engineering, Construction and Architectural Management, 11 (5), pp.323 – 334

Kannan, G., (2011), "Field Studies in Construction Equipment Economics and Productivity", Journal of Construction Engineering and Management, 137 (10), 823-828.

Kazaz, A., and Ulubeyli, S. (2007), “Drivers of productivity among construction workers: a study in a developing country”, Building and Environment, 42(5), 2132-2140.

Ke, Y. J., Wang, S. Q., Chan, A. P. C., and Cheung, E. (2009), “Research trend of Public-Private-Partnership (PPP) in construction journals”. J. Constr. Eng. Manage., 10.1061/(ASCE)0733-9364(2009)135:10 (1076), 1076–1086.

Kenley.R (2014), “Productivity improvement in the construction process”, Construction Management and Economics, Vol. 32 Iss. 6, pp. 489-494.

Lam, S., and Tang, C. (2003), “Motivation of survey employees in construction projects”, J. Geospatial Eng., 5(1), 61–66.

Leonard, C. A. (1987), “The effect of change orders on productivity”, Revay and Acssociates ltd, Canada 6(2), 1-3.

Liao, P. C., O’Brien, W. J., Thomas, S. R., Dai, J., and Mulva, S. P. (2011), “Factors affecting engineering productivity”, J. Manage. Eng., 10.1061/(ASCE)ME.1943-5479.0000059, 229–235.

Lin, C. L., and Huang, H. M. (2010), “Improved baseline productivity analysis techniqu.”, J. Constr. Eng. Manage., 10.1061/(ASCE)CO .1943-7862.0000129, 367–376.

Liu, M., Ballard, G., and Ibbs, W. (2011), “Work flow variation and labor productivity: Case study”, J. Manage. Eng., 10.1061/(ASCE)ME.1943- 5479.0000056, 236–242.

Loosemore, M. (2014), “Improving construction productivity: a subcontractor's perspective, Engineering, Construction and Architectural Management, 21 (3), pp. 245 – 260.

Love, P. E. D., and Smith, J. (2003), “Benchmarking, benchaction, and benchlearning: rework mitigation in projects”, J. Manage. Eng., 10.1061/(ASCE)0742-597X(2003)19:4(147), 147–159.

Mahamid, I. (2013),"Contractors perspective toward factors affecting labor productivity in building constructio.", Engineering, Construction and Architectural Management, Vol. 20 Iss 5 pp. 446 – 460.

McMeeken, R., (2008), “Construction 2025” Building magazine. 8, May.

Maloney, W. (1986), “Understanding motivation”, J. Manage. Eng., 2(4), 231–245.

Myers, D. (2013). Construction Economics; a new approach. Routledge.

Odeh, A.M. and Battaineh, H.T. (2002), “Causes of construction delay: traditional contracts”, International Journal of Project Management, 20, 67-73.

Naoum, S. and Hackman, J. (1996) “Do site managers and the head office perceive productivity factors differently? Journal of Engineering, Construction and Architectural

Management, 3(1), March 1996, pp. 147-160.

Naoum, S. (2011). People and Organizational Management in Construction, 2nd edition,

ICI Publishers, London,.ISBN 978-0-7277-4151-6,

Nasirzadeh, F. and Nojedehi, P. (2013) ,“Dynamic modelling of labour productivity in construction projects”, International Journal of Project Management Vol. 31 pp. 903–911

Ng, S T, Luu, D T, Chen, S E and Lam, K C (2002), “Fuzzy Membership Functions of Procurement Selection Criteria”, Construction Management and Economics, 20(3), pp. 285–296

Nicholls, C. and Langford, D. (1987), “Motivation of site managers.” Technical Information Service, CIOB, 78.

Park, H., Thomas, S. R., and Tucker, R. L. (2005), “Benchmarking of construction productivity”, J. Constr. Eng. Manage., 10.1061/(ASCE) 0733-9364(2005)131:7(772), 772–778.

Pheng, L. S., and Tan, S. K. L. (1998), “How ‘just-in-time’ wastages can be quantified: case study of a private condominium project”, Construction Management and Economics, 16(6), 621-635.

Pradhan, A. and Akinci, B. (2012) ”Planning-Based Approach for Fusing Data from Multiple Sources for Construction Productivity Monitoring”. J. Comput. Civ. Eng., 26(4), 530–540. Technical Papers

Proverbs, D. G., Holt, G. D., and Olomolaiya, P. O. (1999), “Construction resource/method factors influencing productivity for high rise concrete construction”, Journal of Construction Management and Economics, 17(5), 577-587.

Ranasinghe, U., Ruwanpura, J., and Liu, X. (2012), ”Streamlining the Construction Productivity Improvement Process with the Proposed Role of a Construction Productivity Improvement Officer”, J. Constr. Eng. Manage., 138(6), 697–706.

Rojas, E. M., and Aramvareekul, P. (2003), “Is construction labor productivity

really declining?”, J. Constr. Eng. Manage., 10.1061/(ASCE) 0733-9364(2003)129:1(41), 41–46.

Rivas, R. A., Borcherding, J. D., González, V., and Alarcón, L. F. (2011), “Analysis of factors influencing productivity using craftsmen questionnaires: Case study in a Chilean construction company”, J. Constr. Eng. Manage., 10.1061/(ASCE)CO.1943-7862.0000274, 312–320.

Ruthankoon, R., and Ogunlana, S. (2003), “Testing Herzberg’s two-factor theory in the Thai construction industry”, Eng., Constr. Archit. Manage., 10(5), 333–341.

Sanders, S. R., Thomas, H. R., and Smith, G. R. (1989), An analysis of factors affecting labor productivity in masonry construction,  PTI Rep. 9003, Pennsylvania Transportation Institute, University Park, PA.

Sanvido, V. and Paulson, B. (1992), ”Site‐Level Construction Information System”,  J. Constr. Eng. Manage., 118(4), 701–715.

# Shahata, K., and Zayed, T. (2011), Simulation-based life cycle cost modeling and maintenance plan for water mains,  Taylor Frances online. .1080/15732479.2011.552509, pages 403-415

Smith, A. D. (1987), Measuring on-site production,  Transactions of the American Association of Cost Engineers, 31st Annual Meeting, Atlanta.

Singh, S. P. (2010), Factors affecting the productivity of construction operations in the United Arab Emirates,  M.S. thesis, Heriot-Watt Univ., Edinburgh, U.K.

Stainer, A.,(1997), "Logistics ‐ a productivity and performance perspective", Supply Chain Management: An International Journal, Vol. 2 Iss: 2, pp.53 – 62.

Thomas, H. R., Sanvido, V. and Sanders, R., (1989),“Impact of material manangement on productivity – a case study, “Journal of Construction Engineering and Management, ASCE, 115(3), 370-384.

Thomas, H. R. (1992), “ Effects of scheduled overtime on labor productivity”,  Journal of Construction Engineering and Management, ASCE, 118(1), 60-76.

Thomas, H. R., and Napolitan, C. L. (1995), “Quantitative effects of organizational changes on labor productivity.” Journal of Construction Engineering and Management, ASCE, 121(3), 290-296.

Thomas, H. R., Riley, D. R., and Sanvido, V. E. (1999), “Loss of labor productivity due to delivery methods and weather”, J. Constr. Eng. Manage., 125(1), 39–46.

Thomas, H. R., and Zavrski, I. (1999), “Construction baseline productivity: Theory and practice”, J. Constr. Eng. Manage., 10.1061/(ASCE)0733- 9364(1999)125:5(295), 295–303.

Thomas, H. R., Horman, M. J., Minchin, R. E., and Chen, D. (2003),“Improving

labor flow reliability for better productivity as lean construction principle”, J. Constr. Eng. Manage., 10.1061/(ASCE)0733-9364(2003) 129:3(251), 251–261.

Thomas, H. R., and Horman, M. J. (2006), “Fundamental principles of workforce management”, J. Constr. Eng. Manage., 132(1), 97–104.

Yeung, J., Chan, A., Chan, D., Chiang, Y., and Yang, H. (2013), “Developing a benchmarking model for construction projects in Hong Kong”, J. Constr. Eng. Manage., 10.1061/(ASCE)CO.1943-7862.0000622,705–716.

Yi, W. and Chan, A. (2014), ”Critical Review of Labour Productivity Research in Construction Journals”, J. Manage. Eng., 30(2), 214–225.

Tsai, C. C., and Wen, M. C. L. (2005). “Research and trends in science education from 1998 to 2002: A content analysis of publications in selected journals”, Int. J. Sci. Educ., 27(1), 3–14. 224.

Watkins, M., Mukherjee, A., Onder, N., and Mattila, K. (2009), ”Using Agent-Based Modeling to Study Construction Labor Productivity as an Emergent Property of Individual and Crew Interactions”, J. Constr. Eng. Manage., 135(7), 657–667.

Xue, X., Shen, O., Wang, Y., and Lu, J., (2008), “Measuring the Productivity of the Construction Industry in China by Using DEA-Based Malmquist Productivity Indices”, J. Constr. Eng. Manag., 10.1061/_ASCE_0733-9364_2008_134:1,_64-71

Zhao, T. and Dungan, J. (2014), ”Improved Baseline Method to Calculate Lost Construction Productivity,”, J. Constr. Eng. Manage., 140(2), 06013006.

Zink, D. A. (1990), “ Impacts and construction inefficiency”, Cost Engineering, 32(11), 21–23.